## Bug Testing
Durkha Pet Web APP
Created By | Saurav
Created Date
Reviewed BY
Reviewed Date
Reviewers Comment
Pre Condition
Executed BY | Saurav
Executed Date
Browser/APP | Chrome / Safari / Brave
Devices | Desktop / Mobile
Version | -
Test Status | Pass
Bug ID | Bug Description | Steps to reproduce | Ecpected Result | Actual Result | Pre Condition | Ecpected Result | Actual Result | Status | Bug Severiety
B001 | Product image fails to load on detail page | 1. Navigate to product detail page 2. Observe if images load | Product images load correctly and are visible without broken links | Image placeholders show broken links or no image displayed | Product images uploaded in database | Product images load correctly and are visible without broken lin | Image placeholders show broken links or no image displayed | Closed | High
B002 | "Add to Cart" button not functional | 1. Open product detail page 2. Click "Add to Cart" button 3. Observe if item is added to cart | Item is successfully added to the cart | Clicking button does not add item to cart | Cart functionality active | Item is successfully added to the cart | Clicking button does not add item to cart | Closed | Critical
B003 | Incorrect password error message not displayed | 1. Go to login page 2. Enter valid email and incorrect password 3. Submit and observe error message | Error message displayed: "Incorrect password" | No error message displayed; page reloads without feedback | Account with entered email exists | Error message displayed: "Incorrect password" | No error message displayed; page reloads without feedback | Closed | Meduim
B004 | Checkout accessible with an empty cart | 1. Navigate to cart page with an empty cart 2. Attempt to proceed to checkout | Checkout button is disabled, or user is prompted with a message: "Your cart is empty" | User proceeds to checkout page without items in cart | Cart is empty | Checkout button is disabled, or user is prompted with a message: "Your cart is empty" | User proceeds to checkout page without items in cart | Closed | High
B005 | Search does not return relevant results | 1. Enter valid product name in search bar 2. Observe results | Relevant results are displayed | No relevant results shown, or results are incorrect | Search feature enabled | Relevant results are displayed | No relevant results shown, or results are incorrect | Closed | Meduim
B006 | Contact form submission fails | 1. Go to Contact Us page 2. Fill out form 3. Submit and observe confirmation or error message | Form is submitted successfully; confirmation message displayed | Submission fails with error message or no response | Contact form active | Form is submitted successfully; confirmation message displayed | Submission fails with error message or no response | Closed | Meduim
B007 | Page layout is not responsive on mobile | 1. Open website on mobile device 2. Navigate through pages and observe layout | All elements aligned properly on mobile screen without cut-offs or overflow issues | Elements appear misaligned or overflow on screen | Mobile view active | All elements aligned properly on mobile screen without cut-offs or overflow issues | Elements appear misaligned or overflow on screen | Closed | High
B008 | Duplicate items do not update cart quantity | 1. Add an item to cart 2. Add the same item again 3. Check if quantity is updated | Quantity is updated for duplicate items | Duplicate items appear as separate line items instead | Cart functionality active | Quantity is updated for duplicate items | Duplicate items appear as separate line items instead | Closed | Low
B009 | Profile update does not save | 1. Log in as user 2. Go to profile settings 3. Update profile info 4. Save and observe changes | Profile saves with new data and displays updated information on profile page | Changes not saved, and no error message displayed | User logged in | Profile saves with new data and displays updated information on profile page | Changes not saved, and no error message displayed | Closed | Meduim
B010 | Session timeout does not log out inactive users | 1. Log in with valid credentials 2. Remain inactive for specified session timeout period | Session expires after timeout period; user is logged out automatically | Session remains active beyond timeout period | Valid session settings | Session expires after timeout period; user is logged out automatically | Session remains active beyond timeout period | Closed | High